## Overview
KUWAIT WHATSAPP GROWTH ENGINE - FULL SPRINT PLAN (S1-S15)
15 Sprints ¦ 30 Weeks ¦ 29 DB Tables ¦ ~105 API Endpoints ¦ 132 Source Files ¦ 17 Services
# | Sprint Name | Weeks | Duration | Phase | Status | Tasks | Key Deliverables | Priority
1 | Foundation & Auth | W1-W2 | 2 wks | Phase 1 | DONE | 12 | JWT, RBAC, Docker 7 svc, PostgreSQL RLS, Redis, Celery, Next.js 15 | P0
2 | Core CRM | W3-W4 | 2 wks | Phase 2 | DONE | 9 | Contacts CRUD, tags, custom fields, CSV import, search, data table | P0
3 | WhatsApp Integration | W5-W6 | 2 wks | Phase 3 | DONE | 10 | Cloud API provider, webhooks, conversations, messages, WebSocket inbox | P0
4 | Smart Routing & Automation | W7-W8 | 2 wks | Phase 4 | DONE | 9 | 4-factor routing, automation rules (7 ops, 8 actions), Celery execution | P0
5 | AI Dialect Engine | W9-W10 | 2 wks | Phase 5 | DONE | 8 | Kuwaiti dialect detection, intent (10 types), sentiment, Claude API | P1
6 | Sales Pipeline | W11-W12 | 2 wks | Phase 6 | DONE | 8 | Pipeline CRUD, kanban board, deals, stages, activity log, drag-drop | P0
7 | Payments & Billing | W13-W14 | 2 wks | Phase 7 | DONE | 9 | Tap K-Net/Visa/MC, subscriptions, invoices, plan limits, webhook | P0
8 | Shipping Integration | W15-W16 | 2 wks | Phase 8 | DONE | 8 | Carrier abstraction, Aramex, tracking events, WhatsApp notifications | P1
9 | Landing Pages | W17-W18 | 2 wks | Phase 9 | DONE | 8 | Block editor (8 types), publish, public pages, conversion tracking | P1
10 | Analytics Dashboard | W19-W20 | 2 wks | Phase 10 | DONE | 6 | Dashboard KPIs, message/pipeline/team/LP/automation stats | P1
11 | Compliance & Audit | W21-W22 | 2 wks | Phase 11 | DONE | 7 | Audit logs, 8-check compliance, data residency report, security list | P0
12 | Optimization & Hardening | W23-W24 | 2 wks | Phase 12 | DONE | 7 | Redis cache, Prometheus metrics, 5 periodic tasks, Alembic, .env | P1
13 | Production Readiness | W25-W26 | 2 wks | Deploy | TODO | 18 | Secrets, SSL, AWS me-south-1, CI/CD, RDS, load test, DNS, monitoring | P0
14 | UI Polish & i18n | W27-W28 | 2 wks | Frontend | TODO | 14 | shadcn/ui, Arabic RTL, translations, responsive, dark mode, toasts | P1
15 | Testing & QA | W29-W30 | 2 wks | Quality | TODO | 12 | Unit tests (7 services), integration (3 flows), OWASP security audit | P0
TOTAL (15 SPRINTS, 30 WEEKS)

## S1 - FOUNDATION & AUTH
SPRINT 1: FOUNDATION & AUTH (W1-W2)
12 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Set up project structure (backend/frontend/docker) | DevOps | P0 | DONE | Monorepo with backend/, frontend/, docker/ | 2h
2 | Create FastAPI app factory with lifespan | Backend | P0 | DONE | main.py: middleware stack, error handlers | 3h
3 | Set up SQLAlchemy 2.0 async + Alembic | Backend | P0 | DONE | Base, UUIDMixin, TimestampMixin, TenantMixin | 3h
4 | Create User, Role, UserRole, APIKey models | Backend | P0 | DONE | auth.py: smart routing fields on User | 3h
5 | Create Company model with encrypted config | Backend | P0 | DONE | WhatsApp, Twilio, Tap config fields | 2h
6 | Build JWT auth (access 15m + refresh 7d) | Backend | P0 | DONE | security.py: bcrypt 12 rounds, HS256 | 4h
7 | Build auth service (register, login, refresh, me) | Backend | P0 | DONE | auth_service.py: 4 endpoints | 4h
8 | Create RBAC (5 roles, 30+ permissions) | Backend | P0 | DONE | permissions.py: ROLE_PERMISSIONS mapping | 2h
9 | Create Docker Compose (7 services) | DevOps | P0 | DONE | api, frontend, db, redis, minio, celery x2 | 4h
10 | Set up PostgreSQL with RLS helpers | Database | P0 | DONE | init.sql: uuid-ossp, pg_trgm, btree_gin | 2h
11 | Create Next.js 15 with RTL fonts + Tailwind v4 | Frontend | P0 | DONE | Inter + Noto Sans Arabic, globals.css | 3h
12 | Create login, register, forgot-password pages | Frontend | P0 | DONE | Auth store (Zustand), API client (Axios) | 4h

## S2 - CORE CRM
SPRINT 2: CORE CRM (W3-W4)
9 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create Contact, Tag, ContactTag models | Backend | P0 | DONE | SoftDelete, search index, status index | 3h
2 | Create CustomField, CustomFieldValue models | Backend | P0 | DONE | 5 types: text/number/date/select/boolean | 2h
3 | Build contact service (CRUD, search, filter, sort, paginate) | Backend | P0 | DONE | ilike search on name/phone/email, tag filter | 5h
4 | Build tag service (CRUD) | Backend | P0 | DONE | Color-coded, company-unique names | 2h
5 | Build custom field service | Backend | P0 | DONE | Sort ordering, field type validation | 2h
6 | Create contacts API (6 endpoints + bulk + import) | Backend | P0 | DONE | /v1/contacts, /v1/tags, /v1/custom-fields | 4h
7 | Build CSV import Celery task | Backend | P1 | DONE | Flexible column mapping, batch commits | 3h
8 | Build contacts list page with data table | Frontend | P0 | DONE | Search, filters, sort, pagination, checkboxes | 5h
9 | Build contact detail/edit page | Frontend | P0 | DONE | Inline edit, tag selection, custom fields | 4h

## S3 - WHATSAPP INTEGRATION
SPRINT 3: WHATSAPP INTEGRATION (W5-W6)
10 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create Conversation model | Backend | P0 | DONE | Status, assignment, last_msg cache, unread | 2h
2 | Create Message + MessageTemplate models | Backend | P0 | DONE | Direction, delivery status, external_id | 3h
3 | Build WhatsApp Cloud API provider | Backend | P0 | DONE | Send text/media/template/interactive/location | 5h
4 | Build webhook receiver (GET verify + POST events) | Backend | P0 | DONE | Parse messages + status updates from Meta | 4h
5 | Build conversation service | Backend | P0 | DONE | get_or_create, add_message, delivery tracking | 4h
6 | Build WebSocket manager (per-company broadcast) | Backend | P0 | DONE | connect, disconnect, broadcast_to_company | 3h
7 | Create messaging Celery task | Backend | P0 | DONE | Async send via Cloud API with retry | 2h
8 | Create conversation/message API (7 endpoints) | Backend | P0 | DONE | List, detail, send, messages, update status | 4h
9 | Build shared inbox page (split-pane) | Frontend | P0 | DONE | Conv list (left), chat thread (right) | 5h
10 | Add WebSocket endpoint to main.py | Backend | P0 | DONE | /ws?token=jwt with ping/pong | 1h

## S4 - SMART ROUTING & AUTOMATI
SPRINT 4: SMART ROUTING & AUTOMATION (W7-W8)
9 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Build smart routing engine | Backend | P0 | DONE | Relationship (40pts), skills (30), load (40), online (10) | 5h
2 | Create Automation, AutomationAction, AutomationLog models | Backend | P0 | DONE | Trigger + conditions JSONB + actions ordered | 3h
3 | Build automation service (CRUD) | Backend | P0 | DONE | Create, update, toggle, delete, logs | 3h
4 | Build condition evaluation engine | Backend | P0 | DONE | 7 operators: equals/contains/gt/lt/in/starts/not | 4h
5 | Build action execution engine | Backend | P0 | DONE | 8 types: auto_reply/tag/status/score/assign/template/webhook | 4h
6 | Create automation Celery task | Backend | P0 | DONE | asyncio.run with fresh engine per task | 2h
7 | Create automation API (6 endpoints) | Backend | P0 | DONE | CRUD + toggle + logs | 3h
8 | Integrate routing into webhook handler | Backend | P0 | DONE | Auto-assign on new inbound conversation | 1h
9 | Build automation builder page | Frontend | P0 | DONE | Trigger select, conditions, action config, logs panel | 4h

## S5 - AI DIALECT ENGINE
SPRINT 5: AI DIALECT ENGINE (W9-W10)
8 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create AIConversationContext model | Backend | P0 | DONE | Dialect, intent, sentiment, history JSONB, insights | 2h
2 | Build dialect detection (rule-based fallback) | Backend | P0 | DONE | Arabic ratio + Kuwaiti markers (10+ words) | 3h
3 | Build intent classification (10 categories) | Backend | P0 | DONE | pricing/purchase/support/complaint/greeting/... | 3h
4 | Build sentiment analysis | Backend | P0 | DONE | positive/negative/neutral/mixed, -1.0 to 1.0 | 2h
5 | Build Claude API integration | Backend | P1 | DONE | System prompt with Kuwaiti dialect knowledge | 3h
6 | Build AI response generator | Backend | P1 | DONE | Culturally appropriate, customer dialect match | 2h
7 | Create AI API (3 endpoints) | Backend | P0 | DONE | POST /analyze, GET /context, POST /suggest | 2h
8 | Integrate AI into webhook flow (Celery) | Backend | P0 | DONE | Auto-analyze every inbound message | 1h

## S6 - SALES PIPELINE
SPRINT 6: SALES PIPELINE (W11-W12)
8 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create Pipeline, PipelineStage models | Backend | P0 | DONE | Ordered stages with color, is_won/is_lost | 2h
2 | Create Deal, DealActivity models | Backend | P0 | DONE | Value DECIMAL(12,3), position, custom_data JSONB | 3h
3 | Build pipeline service (CRUD + stages) | Backend | P0 | DONE | Add/remove stages, default pipeline | 3h
4 | Build deal service (CRUD + move + activities) | Backend | P0 | DONE | Auto-log stage/value/status changes | 4h
5 | Build kanban board endpoint | Backend | P0 | DONE | Deals grouped by stage with totals | 2h
6 | Create pipeline API (13 endpoints) | Backend | P0 | DONE | Pipelines, stages, deals, board, activities, notes | 4h
7 | Build kanban board UI with drag-drop | Frontend | P0 | DONE | Color columns, deal cards, HTML5 DnD | 5h
8 | Build create deal dialog | Frontend | P0 | DONE | Title, value (KWD), stage selector | 2h

## S7 - PAYMENTS & BILLING
SPRINT 7: PAYMENTS & BILLING (W13-W14)
9 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create Plan model (global) | Backend | P0 | DONE | Pricing KWD, feature limits, flags | 2h
2 | Create Subscription, Invoice, Payment models | Backend | P0 | DONE | Lifecycle, INV-YYYYMM-NNNN, Tap refs | 3h
3 | Build Tap Payments service | Backend | P0 | DONE | K-Net/Visa/MC source mapping, 3D Secure | 4h
4 | Build subscription service | Backend | P0 | DONE | Create, change plan, cancel, auto-invoice | 4h
5 | Build charge creation with redirect URL | Backend | P0 | DONE | POST /charges returns payment_url | 2h
6 | Build Tap webhook handler | Backend | P0 | DONE | CAPTURED/FAILED -> update payment + invoice | 2h
7 | Create payment API (10 endpoints) | Backend | P0 | DONE | Plans, subscription, invoices, charges, webhook | 3h
8 | Seed default plans (Starter/Growth/Enterprise) | Database | P1 | DONE | 9.9/29.9/79.9 KWD monthly | 30m
9 | Build billing page with plan cards | Frontend | P0 | DONE | Monthly/yearly toggle, invoice table | 4h

## S8 - SHIPPING INTEGRATION
SPRINT 8: SHIPPING INTEGRATION (W15-W16)
8 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create ShippingProvider, Shipment, TrackingEvent models | Backend | P0 | DONE | Carrier config, COD, 7 status states | 3h
2 | Build abstract ShippingCarrier interface | Backend | P0 | DONE | create_shipment, track, cancel | 2h
3 | Build Aramex Kuwait implementation | Backend | P0 | DONE | Real API + mock mode for dev | 3h
4 | Build shipment service (CRUD + tracking) | Backend | P0 | DONE | Auto-log events on status change | 4h
5 | Build carrier tracking refresh (poll API) | Backend | P1 | DONE | POST /refresh polls carrier | 2h
6 | Build WhatsApp tracking notification task | Backend | P0 | DONE | 7 status message templates via Celery | 2h
7 | Create shipping API (8 endpoints) | Backend | P0 | DONE | Providers, shipments, tracking, refresh | 3h
8 | Build shipment management page | Frontend | P1 | DONE | List, status badges, tracking timeline | 3h

## S9 - LANDING PAGES
SPRINT 9: LANDING PAGES (W17-W18)
8 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create LandingPage model | Backend | P0 | DONE | Blocks JSONB, settings, WhatsApp CTA, SEO | 2h
2 | Build landing page service (CRUD + publish) | Backend | P0 | DONE | Slug uniqueness, visit/conversion counters | 3h
3 | Build public page endpoint (no auth) | Backend | P0 | DONE | GET /public/{slug} auto-increments visits | 2h
4 | Build conversion recording endpoint | Backend | P0 | DONE | POST /public/{slug}/convert | 1h
5 | Build analytics endpoint | Backend | P1 | DONE | Conversion rates per page | 1h
6 | Create landing pages API (10 endpoints) | Backend | P0 | DONE | CRUD + publish + unpublish + public + convert | 3h
7 | Build page list with stats cards | Frontend | P0 | DONE | Grid, status badges, visit/conversion rates | 3h
8 | Build block editor page | Frontend | P0 | DONE | 8 block types, add/remove/reorder, inline edit | 5h

## S10 - ANALYTICS DASHBOARD
SPRINT 10: ANALYTICS DASHBOARD (W19-W20)
6 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Build analytics service (dashboard stats) | Backend | P0 | DONE | Contacts, conversations, messages, deals | 3h
2 | Build message volume stats (daily + delivery) | Backend | P0 | DONE | GROUP BY date + direction | 2h
3 | Build pipeline stats (stages, win rate, avg deal) | Backend | P0 | DONE | Outer join stages with deal aggregates | 2h
4 | Build team performance stats (per-agent) | Backend | P1 | DONE | Messages sent, convs, deals won, revenue | 2h
5 | Build landing page + automation stats | Backend | P1 | DONE | Visits, conversions, execution counts | 1h
6 | Build analytics dashboard page | Frontend | P0 | DONE | KPI cards, pipeline chart, team table, LP stats | 5h

## S11 - COMPLIANCE & AUDIT
SPRINT 11: COMPLIANCE & AUDIT (W21-W22)
7 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Create AuditLog model (immutable) | Backend | P0 | DONE | Who, what, resource, changes JSONB, IP | 2h
2 | Build audit service (log + query) | Backend | P0 | DONE | Filter by action, resource, user | 2h
3 | Build compliance service (8-point checklist) | Backend | P0 | DONE | Data residency, encryption, consent, retention | 3h
4 | Build compliance report generator | Backend | P0 | DONE | Security measures, data summary, frameworks | 2h
5 | Create compliance API (3 endpoints) | Backend | P0 | DONE | GET /status, /report, /audit-logs | 2h
6 | Build compliance dashboard page | Frontend | P0 | DONE | Checklist, residency info, security list, logs | 4h
7 | Build audit log viewer | Frontend | P1 | DONE | Table with action, description, timestamp | 2h

## S12 - OPTIMIZATION & HARDENING
SPRINT 12: OPTIMIZATION & HARDENING (W23-W24)
7 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Build Redis caching layer | Backend | P0 | DONE | get/set/delete/pattern, 5-min TTL, namespaced | 2h
2 | Build Prometheus metrics collector | Backend | P0 | DONE | Counters, histograms (p50/p95/p99), gauges | 3h
3 | Integrate metrics into timing middleware | Backend | P0 | DONE | http_requests_total, http_request_duration | 1h
4 | Create /metrics + /metrics/json endpoints | Backend | P0 | DONE | Prometheus text + JSON format | 1h
5 | Implement 5 periodic Celery beat tasks | Backend | P0 | DONE | analytics, payments, webhooks, auth, templates | 3h
6 | Fix Alembic + generate initial migration | Database | P0 | DONE | alembic.ini, sys.path fix, stamp head | 2h
7 | Create .env file + fix docker-compose gaps | DevOps | P0 | DONE | Nginx service, health checks, beat DB dep | 2h

## S13 - PRODUCTION READINESS
SPRINT 13: PRODUCTION READINESS (W25-W26)
18 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Generate production secrets (JWT, app key, verify token) | Security | P0 | TODO | openssl rand -hex 32 | 1h
2 | Set WhatsApp Cloud API credentials | Integration | P0 | TODO | Register at developers.facebook.com | 2h
3 | Set Tap Payments keys (K-Net, Visa, MC) | Integration | P0 | TODO | tap.company developer portal | 2h
4 | Set Anthropic API key for AI engine | Integration | P1 | TODO | console.anthropic.com | 30m
5 | Configure SSL/TLS (Let's Encrypt + nginx) | Security | P0 | TODO | certbot, TLS 1.3, HSTS headers | 3h
6 | Add HTTPS + gzip + rate limit to nginx | Security | P0 | TODO | ssl_certificate, gzip on, limit_req | 2h
7 | Create docker-compose.prod.yml | DevOps | P0 | TODO | No volumes, env_file, built images, restart | 3h
8 | Set up AWS me-south-1 (EC2 or ECS Fargate) | DevOps | P0 | TODO | Terraform or CloudFormation | 8h
9 | Configure RDS PostgreSQL 16 (multi-AZ) | DevOps | P0 | TODO | Encrypted, automated backups, read replica | 4h
10 | Configure ElastiCache Redis | DevOps | P1 | TODO | Cluster mode, encryption | 2h
11 | Set up S3 bucket (replace MinIO) | DevOps | P1 | TODO | Versioning, lifecycle rules, CORS | 1h
12 | CI/CD deploy pipeline (GitHub Actions) | DevOps | P0 | TODO | Build > push ECR > deploy ECS | 6h
13 | Add container registry push to CI | DevOps | P0 | TODO | ECR or Docker Hub | 2h
14 | Configure Sentry error tracking | Monitoring | P1 | TODO | Set SENTRY_DSN in production | 1h
15 | Set up CloudWatch log aggregation | Monitoring | P1 | TODO | JSON structured logs ready | 4h
16 | Load test with k6 (100 concurrent users) | Testing | P1 | TODO | Target <200ms p95 latency | 4h
17 | Database backup automation | DevOps | P0 | TODO | RDS snapshots + pg_dump cron | 2h
18 | Domain DNS (app.kwgrowth.com) | DevOps | P0 | TODO | A record + CNAME + SSL cert | 1h

## S14 - UI POLISH & INTERNATIONA
SPRINT 14: UI POLISH & INTERNATIONALIZATION (W27-W28)
14 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Initialize shadcn/ui + install core components | UI | P0 | TODO | npx shadcn-ui init; Button, Input, Select | 2h
2 | Add Table, Badge, Card, Dialog, Toast, DropdownMenu | UI | P0 | TODO | Data display + interaction components | 2h
3 | Refactor contacts page with shadcn components | UI | P1 | TODO | Replace inline Tailwind classes | 3h
4 | Refactor inbox with shadcn components | UI | P1 | TODO | Conversation list, message bubbles, input | 3h
5 | Refactor pipeline kanban with @dnd-kit | UI | P1 | TODO | DndContext, SortableContext, proper a11y | 4h
6 | Wire next-intl useTranslations() in all pages | i18n | P0 | TODO | Replace 100+ hardcoded English strings | 4h
7 | Complete Arabic translations (common.json) | i18n | P0 | TODO | All nav, forms, messages, statuses | 3h
8 | Add RTL layout toggle in settings | i18n | P1 | TODO | dir=rtl on html, RTL Tailwind plugin | 2h
9 | Fix RTL layout issues (margins, padding, icons) | i18n | P1 | TODO | Use logical properties ms/me vs ml/mr | 4h
10 | Responsive mobile layout for dashboard | UI | P1 | TODO | Collapsible sidebar, hamburger menu | 4h
11 | Dark mode support | UI | P2 | TODO | CSS variables ready, toggle + prefers-color-scheme | 3h
12 | Loading skeletons for all pages | UX | P2 | TODO | Replace spinners with skeleton placeholders | 2h
13 | Toast notifications on all mutations | UX | P1 | TODO | Success/error toasts on create/update/delete | 2h
14 | Form validation with Zod + react-hook-form | UX | P1 | TODO | All forms: contacts, deals, automations | 3h

## S15 - TESTING & QUALITY ASSURA
SPRINT 15: TESTING & QUALITY ASSURANCE (W29-W30)
12 tasks
# | Task | Category | Pri | Status | Notes / Details | Est.
1 | Unit tests: auth service (register, login, refresh) | Backend | P0 | TODO | pytest + httpx AsyncClient | 3h
2 | Unit tests: contact service (CRUD, search, bulk) | Backend | P0 | TODO | Mock DB with async fixtures | 3h
3 | Unit tests: conversation service + messages | Backend | P0 | TODO | Message creation, status tracking | 3h
4 | Unit tests: automation engine (conditions + actions) | Backend | P0 | TODO | Test all 7 operators, 8 action types | 4h
5 | Unit tests: AI dialect engine (fallback mode) | Backend | P1 | TODO | Kuwaiti/Gulf/MSA/English detection | 2h
6 | Unit tests: pipeline service (deals, stages, board) | Backend | P1 | TODO | Activity logging, kanban grouping | 3h
7 | Unit tests: Tap Payments (mock charges) | Backend | P1 | TODO | Mock httpx, test webhook parsing | 2h
8 | Integration test: full auth flow E2E | Backend | P0 | TODO | Register > login > me > refresh > logout | 2h
9 | Integration test: contact > conversation > message | Backend | P0 | TODO | Create contact, start conv, send, check | 3h
10 | Integration test: webhook > automation pipeline | Backend | P1 | TODO | Inbound msg triggers rule, executes actions | 3h
11 | Frontend component tests (Vitest + RTL) | Frontend | P1 | TODO | Login form, contacts table, inbox | 4h
12 | Security audit: OWASP Top 10 checklist | Security | P0 | TODO | SQLi, XSS, CSRF, broken auth, IDOR | 4h

## Architecture
DATABASE SCHEMA - 29 TABLES
# | Table Name | Module | Mixins | Description
1 | users | Auth | Tenant+Timestamp | JWT auth, profile, smart routing (skills, hours, online)
2 | roles | Auth | UUID+Timestamp | 5 system roles: platform_admin, owner, admin, manager, agent
3 | user_roles | Auth | Junction | User-role many-to-many mapping
4 | api_keys | Auth | Tenant | Scoped API keys with prefix, hash, expiration
5 | companies | Core | UUID+Timestamp | Multi-tenant: name, slug, WhatsApp/Twilio/Tap encrypted config
6 | contacts | CRM | Tenant+SoftDelete | Phone (E.164), email, lead_score, opt_in, source, assigned agent
7 | tags | CRM | Tenant | Color-coded (#hex), company-unique name, description
8 | contact_tags | CRM | Junction | Contact-tag many-to-many
9 | custom_fields | CRM | Tenant | 5 types: text, number, date, select, boolean; sort_order
10 | custom_field_values | CRM | Junction | Contact-field values (text stored)
11 | conversations | Messaging | Tenant | Status (open/closed/pending/snoozed), unread_count, last_msg cache
12 | messages | Messaging | Tenant | Direction (in/out), sender_type, delivery_status, external_id
13 | message_templates | Messaging | Tenant | WhatsApp templates: header, body, footer, buttons, status
14 | automations | Automation | Tenant | Trigger event, conditions JSONB, priority, execution_count
15 | automation_actions | Automation | FK | 8 types: auto_reply/tag/status/score/assign/template/webhook
16 | automation_logs | Automation | Tenant | Execution status, actions_executed, duration_ms, error
17 | ai_conversation_contexts | AI | Tenant | Dialect, intent (+confidence), sentiment (+score), history JSONB
18 | pipelines | Pipeline | Tenant | Named sales pipelines, is_default flag
19 | pipeline_stages | Pipeline | FK | Colored stages, sort_order, is_won/is_lost terminal flags
20 | deals | Pipeline | Tenant+SoftDelete | Value DECIMAL(12,3) KWD, status, position, expected_close
21 | deal_activities | Pipeline | FK | Type: stage_changed/value_changed/status_changed/note_added
22 | plans | Billing | Global | Pricing (monthly/yearly KWD), max_contacts/convs/team/automations
23 | subscriptions | Billing | Tenant | Plan, cycle, period_start/end, cancel_at_period_end
24 | invoices | Billing | Tenant | INV-YYYYMM-NNNN, subtotal/tax/total, line_items JSONB
25 | payments | Billing | Tenant | Tap charge_id, payment_method (knet/visa/mc), card_last_four
26 | shipping_providers | Shipping | Tenant | Carrier (aramex/dhl/fetchr/shipa), credentials, config
27 | shipments | Shipping | Tenant | Tracking#, COD, addresses JSONB, 7 status states, notif tracking
28 | shipment_tracking_events | Shipping | FK | Status, description, location, event_time, raw_data JSONB
29 | landing_pages | Marketing | Tenant+SoftDelete | Blocks JSONB (8 types), slug, WhatsApp CTA, visit/conversion counters
30 | audit_logs | Compliance | Tenant | Immutable: action, resource, changes JSONB, IP, user_agent